Datimpacto

# Terms of Reference Checklist

Datimpacto · MEL Community of Practice Toolkit · Tool 1

Purpose: check a Terms of Reference against the five things it needs to do clearly before it goes out to bidders. When to use: while drafting a ToR, or when reviewing one someone else drafted. Time needed: 20 to 30 minutes.

## The Five Things a Strong ToR Does Clearly

| # | Element | What good looks like | Red flag |
| --- | --- | --- | --- |
| 1 | What and why now | The object, period and geography are named, with a stated reason for commissioning now | A generic description that could fit any program or any year |
| 2 | Who it’s for | Primary users are named, with the decisions they will make from the findings | “Stakeholders” with no names, or no stated use for the findings |
| 3 | Questions or deliverables | A short, prioritized list, not an exhaustive, unranked one | 40 to 50 questions with no ranking, or one vague line covering everything |
| 4 | Boundaries | Geography, timeframe, sample or methodological scope, and a budget ceiling are all stated | No budget ceiling, or no indication of how many interviews, surveys or sites are expected |
| 5 | What “done” looks like | Deliverables, review checkpoints and the approver are named, with review time built into the timeline | Deliverables listed with no review checkpoints, or a timeline with no margin for delays |

The same five things apply to any external consultancy, not only evaluations: a MEL system design contract or a standalone data-collection engagement needs the same five elements stated clearly.

## Timeline Check

Once phases and field activities are drafted, run them through Tool 11 (the timeline feasibility calculator) to check the window in the ToR actually fits the work it asks for.

## Decision

- Ready to publish.

- Needs revision before publishing (list which of the five elements are missing or weak).

## Related Tools

- Tool 10: an AI prompt that runs this checklist against a draft and rates each element. Run it before Tool 7.

- Tool 7: an AI prompt that reads the ToR as a bidder would, before publishing.

- Tool 11: the timeline feasibility calculator.

## References

- UNEG (2010). Quality Checklist for Evaluation Terms of Reference and Inception Reports.

- BetterEvaluation. Manager’s Guide to Evaluation. betterevaluation.org