Datimpacto

# Managing an External Consultancy: One-Page Checklist

Datimpacto · MEL Community of Practice Toolkit · Tool 6

What has to be in place before a final deliverable lands.

## 1. A Clear Terms of Reference

- ☐ Object, period, geography and the reason for commissioning now are stated

- ☐ Primary users and the decisions they will make are named

- ☐ Priority questions or requirements are few and ranked

- ☐ Scope boundaries and a budget ceiling are set

- ☐ Deliverables, review checkpoints and the approver are defined

- ☐ The timeline adds up, with room for delays

## 2. A Defensible Selection Process

- ☐ Pass/fail criteria are published before the call

- ☐ Weighted criteria and their weights are published

- ☐ At least two people score each proposal independently

- ☐ AI triage, if used, stops at a first pass

- ☐ The final decision and its reason are written down

## 3. Milestones Treated as Decision Points

- ☐ Each milestone has a decision question attached

- ☐ The inception report or design document includes a design matrix and sampling or workplan

- ☐ Quality signals are reviewed at each milestone

- ☐ Each review ends with a recorded decision: continue, adjust or redesign

## 4. Active Management While the Work Runs

- ☐ A shared risk and issues log is in use by both sides

- ☐ Changes go through a written change request

- ☐ Check-ins happen every one or two weeks between milestones

- ☐ A contingency margin for time and budget is agreed in the contract

## 5. A Seven-Point Quality Sign-off

- ☐ It answers what was asked

- ☐ The product is trustworthy and limitations are stated

- ☐ The underlying work is sound

- ☐ The findings or outputs are credible

- ☐ Conclusions follow from the evidence

- ☐ The deliverable is usable (who, what and when for each recommendation)

- ☐ It is readable by the team that has to run with it

Detailed versions of each block: Tools 1 to 5. AI prompts for each stage: Tools 7 to 10.